PERSON A — TYLOR

Platform & Data Lead

1-Week MVP Execution Guide · Educational Hardware Builder (OpenAI Week Project)

Toolchain: OpenAI Codex CLI + GitHub Spec-Kit · Companions: mvp-task-tracker.xlsx + Blueprint v2

# 0. Read me first — how this guide works

This guide merges your two source documents (your playbook and your step-by-step timeline) with the two team references (Blueprint v2 and mvp-task-tracker.xlsx) into one self-sufficient runbook for the 7-day sprint. If you follow this document top to bottom, keep the tracker updated, and respect the wait gates, your slice of the project gets built and the three slices integrate on Day 5.

### The code system

- Every task in the sprint has a code. Yours are the A-codes; G-codes (G1–G4) are tasks all three of you do together. Codes map 1:1 to rows in the Tracker sheet of mvp-task-tracker.xlsx (full map in Appendix A).

- Do your codes in order. Never start a task until every code listed under its "Wait for" shows Done in the tracker (column H).

- The moment you finish a task, set its Status cell (column H) to Done — the progress bars and "Blocked" counters update automatically, and someone is usually waiting on you.

- Codes A7 and A8 appear in your timeline but have no rows of their own in the tracker — they are your named share of the group tasks G2 (Day 5 integration) and G3 (Day 6 rehearsals). This guide keeps the codes for clarity and tells you exactly which tracker cell to update instead. G2 and G3 only flip to Done when every person’s share is complete.

### Wait-gate legend

- HARD WAIT — do not start, full stop, until the listed code is Done. Doing the work anyway creates rework and merge conflicts.

- SOFT WAIT — start on time using the listed fallback if the dependency is late, then reconcile when it lands.

### Merge points

You merge to main at five points: A1 (scaffold), G1 (contracts, whole team), A3 (Day 2 EOD — migrations + real schemas package), A5 (Day 4 EOD — retrieval + health, the week’s hardest deadline), and A6 (Day 5, first in the merge train). Every one of your merges unblocks other people the moment it lands — announce each one.

### Toolchain notation (Codex CLI + Spec-Kit)

NOTE — This guide writes Spec-Kit commands as /speckit.xxx. The team default agent is OpenAI Codex CLI in skills mode, where the same commands are invoked as $speckit-xxx — e.g. /speckit.specify becomes $speckit-specify — followed by the exact same prompt text. If anyone prefers Claude Code, the /speckit.xxx form works there as-is. If your Codex build does not show the commands, the prompt files live in .codex/prompts/ in the repo — open the file and paste its contents plus your prompt text into the chat (older Codex builds also pick up prompts copied into ~/.codex/prompts/).

### The 7-day map (whole team)

| Day | Theme | Codes in play |
| --- | --- | --- |
| Day 1 | Foundation and contracts | A1 → G1 (incl. C1) → B1 by lunch → A2, B2 (PM) → C2 by EOD |
| Day 2 | Core engines | A3 (merge), B3, C3 |
| Day 3 | Depth | A4, B4, C4 |
| Day 4 | Feature-complete + merges | A5, B5, C5 — all three merge to main (hard gate for Day 5) |
| Day 5 | Merge train + integration | A6 → B6 → C6, then G2: close all six seams (A7/B7/C7) |
| Day 6 | Rehearsals | G3: two full run-throughs + backup recording + 3D print (A8/B8/C8) |
| Day 7 | Presentation | G4: A opens, C drives demo, B owns the 3D moment |

Why the week is shaped this way: Days 1–4 are deliberately parallel — the Day-1 contract sprint (G1) freezes the interfaces so each of you can build against mocks and fixtures without waiting on each other. Day 4 EOD, all three feature branches must be merge-ready; Day 5 morning is a strict merge train (A → B → C) so conflicts are resolved once, in one direction; the rest of Day 5 replaces every mock with the real implementation (the six "seams"). Days 6–7 are pure de-risking: rehearse, record a backup, present.

# 1. Your mission and your week at a glance

Mission: everything the other two developers stand on — the docker-compose stack, the database, the shared contract package, seed data, and CI. You are upstream of everyone, so you are the project’s critical path all week. You also own the repo scaffold, type the constitution, lead the Day-5 merge train, and run demo ops on stage.

Your subsystem in one sentence: one docker compose up gives any machine a working Postgres+pgvector, local Ollama models, a headless OpenSCAD service, and a typed contract package with mocks that Persons B and C build against.

Your headline: you go first — A1 unblocks the entire team, and A5 (Day 4) is your most important deadline of the week. Protect it above everything.

| Code | When | Task | Waits for | Unblocks | Merge? |
| --- | --- | --- | --- | --- | --- |
| A1 | Day 1, hour 1 | Create + push repo, spec-kit init, pnpm workspaces | — | Everything (G1, all B/C work) | Yes |
| G1 | Day 1, hrs 2–3 | Contract sprint — you type the constitution and chair it | A1 | All parallel work | Yes |
| A2 | Day 1 PM | Spec-kit prompts + compose skeleton (postgres + ollama boot) | G1 | A3 | No |
| A3 | Day 2 | Migrations + model-init + schemas package → MERGE | A2 | B/C go real on schemas; B4 (soft) | Yes |
| A4 | Day 3 | Curate + seed ~50 cited knowledge chunks | A3 (hard); C2 (soft) | A5 | No |
| A5 | Day 4 | /api/retrieve + /api/health → MERGE | A4 | G2 (hard gate) | Yes |
| A6 | Day 5 AM | Merge FIRST in the train | A5 + B5 + C5 all Done | B6 | Yes |
| A7* | Day 5 | Close seams 1–2 with C + demo reset script (*your share of G2) | Merge train done | G2 → Done | No |
| A8* | Day 6 | Demo ops + backup recording (*your share of G3) | G2 | G4 | No |
| G4 | Day 7 | Open (2 min) + run ops; DEMO_SAFE_MODE in reach | G3 | — | No |

# 2. How you will use Codex + Spec-Kit this week

Spec-Kit turns Codex from a chat assistant into a spec-driven build pipeline. You run its stages in order inside a Codex session launched from the repo root. Each stage writes real artifacts into the repo (under .specify/ and your feature directory), so the work is reviewable and resumable.

| Stage | Command (Codex skills mode) | What it produces / how you use it this week |
| --- | --- | --- |
| Constitution | $speckit-constitution | Project-wide non-negotiable principles. Run once, by Person A, during G1. Every later stage checks itself against it. |
| Specify | $speckit-specify | Your feature spec (the WHAT and WHY). You paste the prepared prompt from this guide — it is already written; do not improvise it. |
| Plan | $speckit-plan | The technical plan (the HOW): stack, packages, structure. Again, paste the prepared prompt. |
| Tasks | $speckit-tasks | An ordered, dependency-aware task list. Review and prune it — the spec describes the full feature; the tracker defines this week. Pruning notes are in your task blocks below. |
| Analyze (optional) | $speckit-analyze | Cross-checks spec / plan / tasks for gaps before you build. Worth 5 minutes if time allows. |
| Implement | $speckit-implement | Codex executes the task list. In this sprint, treat it as a steered pair-programmer, not a one-shot: run it after Tasks, point it at the current day’s slice ("do tasks 1–4: the compose skeleton"), review every diff, commit at each passing checkpoint, and resume the next day. Never let it run unattended past a merge deadline. |

NOTE — One-time setup: specify init was run by Person A with --ai codex, so the command files ship inside the repo — cloning is all B and C need. specify check verifies your local tools. If a command is missing or misbehaves, specify self upgrade updates the CLI; regenerating command files is Person A’s call, not yours.

# 3. Day 0 — set up before the sprint (the evening before Day 1)

You cannot afford to burn Day 1’s first hour on installs. Have all of this working the night before:

# uv (Python tool manager) — needed by spec-kit curl -LsSf https://astral.sh/uv/install.sh ¦ sh # OpenAI Codex CLI (the team agent) — then sign in with your ChatGPT account npm install -g @openai/codex codex login # verify afterwards: codex --version # Node 20+, pnpm, git + GitHub CLI, Docker npm install -g pnpm gh auth login # verify: gh auth status

- Python 3.11+, and Docker Desktop / Engine with GPU support enabled (NVIDIA Container Toolkit or ROCm equivalent).

- Spec-Kit CLI (you are the only one who must have it — B and C get the in-repo command files when they clone):

uv tool install specify-cli --from git+https://github.com/github/spec-kit.git specify check # verifies git, agents, and tools are visible

- Decide the GitHub org/owner for the repo and confirm all three accounts have push access.

- Identify the demo machine now (12–16GB VRAM). You need it Day 2 (A3 GPU verification) and Day 6 (A8 demo ops). If it is a different box than your dev machine, arrange physical/remote access today.

- Skim the Blueprint’s "Locked Architecture Decisions" table once more — you are the person who enforces them.

# 4. Day-by-day playbook

## A1 — Create and push the repo (Day 1, first hour)

| When | Day 1, the very first hour |
| --- | --- |
| Wait for | Nothing — you go first |
| Unblocks | Everything. B and C cannot even clone until A1 is Done |
| Merge to main? | Yes (this creates main) |
| Tracker | Set A1 → Done (cell H7) the second the push succeeds, then message B and C |

Why it matters: the whole team is idle until this lands. There is no fallback for A1 — if anything fights you (usually gh auth or org permissions), ask for help after 20 minutes rather than debugging alone.

### Do this

- Initialize the project with Spec-Kit for the Codex agent: specify init hardware-builder --ai codex (add --skills if your spec-kit version supports it, so commands register as $speckit-* skills). Then cd hardware-builder and verify ls .specify shows templates and scripts, and the Codex command files exist (.codex/).

- First commit: git init && git add -A && git commit -m "chore: spec-kit scaffold".

- Create and push the remote: gh repo create <org>/hardware-builder --private --source=. --push.

- Protect main (require PR + 1 review) with the gh api call below. enforce_admins=false is deliberate — it leaves you an emergency bypass for the Day-5 merge train.

- Scaffold the monorepo skeleton (commands below), commit, push.

- Mark A1 Done (H7) and message B and C: "repo is live, clone now, G1 starts in 10."

gh api repos/<org>/hardware-builder/branches/main/protection -X PUT \ -f required_pull_request_reviews[required_approving_review_count]=1 \ -F enforce_admins=false -f restrictions= -f required_status_checks= pnpm init mkdir -p apps/web packages/schemas packages/solver packages/agents \ infra ingestion assets/templates assets/cad-seed # pnpm-workspace.yaml listing: apps/* and packages/*

### Done when

- B and C can git clone and pnpm install succeeds on their machines.

- main is protected; the workspace folders exist; A1 is Done in the tracker.

## G1 — Contract sprint, you chair it (Day 1, hours 2–3)

| When | Day 1, hours 2–3 — timeboxed to 2 hours |
| --- | --- |
| Wait for | A1 (hard) |
| Unblocks | All parallel work for the entire week |
| Merge to main? | Yes — schemas, mocks, fixtures, constitution all land on main |
| Tracker | Set G1 → Done (H8); C simultaneously sets C1 → Done (H10) for the schema subset C defined |

Why it matters: this meeting freezes the interfaces so three people can build in parallel against mocks for four days. It is the highest-leverage two hours of the week. Your special power here: when a field is contested and the clock is running, you decide — unresolved fields get a TODO default and the sprint moves on.

### Do this

- Launch Codex in the repo root (codex) with the other two watching, and run the constitution command with the full prompt below: $speckit-constitution (Claude Code: /speckit.constitution).

- Review Codex’s constitution output together for 10 minutes max, then commit: git add -A && git commit -m "docs: project constitution" && git push. B will push hardest on principles 1 and 8; C on 2, 4 and 7 — let them.

- Co-author packages/schemas — all three of you, live, in one editor session: zod schemas + fixture files + mocks per the ownership table below. Rules everyone agrees to out loud: schema changes require review from all three, and every producer ships a mock in `packages/schemas/mocks/`.

- Two decisions that must not leave the room undecided: the coordinate convention for AssemblyTransform (Z-up, parent-relative — B writes it into the schema doc comment) and mandatory citations on every RetrievalResult chunk (C’s requirement of you).

- Commit and push to main; then everyone creates their feature branch. Yours: git checkout -b feature/001-platform-data && git push -u origin feature/001-platform-data.

Prompt — paste after $speckit-constitution (you type this, verbatim) Create principles for a self-hosted, fully-local educational hardware-building platform. Enforce the following non-negotiables: 1. ACCURACY OVER GENERATION: The product teaches physical construction, so physically wrong output is a critical defect. LLMs must never emit raw spatial coordinates, transform matrices, or electrical values as free text. All spatial math comes from deterministic solvers operating on CAD metadata; all generated 3D geometry comes from parameterized templates compiled and validated by headless OpenSCAD; all factual claims in lessons must be grounded in retrieved sources with citations stored alongside the content. 2. STRUCTURED LLM I/O EVERYWHERE: Every LLM call declares an explicit JSON schema, requests JSON-mode output, validates the response with zod, retries once with the validation error injected into the prompt, and falls back to a deterministic default or a user-facing error after that. No agent may parse free-form model prose. Temperature <= 0.3 for structural outputs. 3. LOCAL-FIRST, CONSUMER-GPU BUDGET: Everything runs via docker-compose on the user's machine. Design for 8-16GB VRAM with quantized models via Ollama. No cloud inference, no external calls at runtime except through the n8n background ingestion pipelines. Embedding models run on CPU. Detect available VRAM at startup and degrade model tier gracefully with an explicit user-visible warning. 4. SAFETY GATES ARE HARD BLOCKS: Projects or steps involving mains AC voltage, LiPo charging, or other flagged hazards must be classified at research time and hard-blocked in Beginner mode (not merely warned). Every step carries a safety category; safety callouts render before instructions, never after. 5. SINGLE DATABASE, TYPED BOUNDARIES: PostgreSQL with pgvector is the only datastore. n8n pipelines never write directly to tables; they terminate in a versioned upsert API owned by the app. All API and SSE payloads are zod-typed and shared between server and client from one schema package. 6. TESTING STANDARDS: Deterministic components (spatial solver, template parameter validation, schema validation, inventory matching SQL) require unit tests with real fixture CAD files. LLM-dependent paths require contract tests that validate output schema conformance using recorded fixtures, plus at least one live smoke test per agent runnable via a make target. The OpenSCAD compile-validate loop must have tests covering compile failure, zero-volume meshes, and out-of-bounds parameters. CI must pass without a GPU (mock Ollama with fixtures). 7. UX CONSISTENCY AND COGNITIVE LOAD: The UI is organized in five fixed tabs (Dashboard, Inventory, Workshop, 3D Mech View within Workshop, Gallery). Socratic checkpoints gate step progression and can never be skipped in Beginner mode. All long-running agent work streams progress to the UI via SSE; no operation over 2 seconds may run without visible streamed status. Beginner/Intermediate is a single flag threaded through all agents, never forked logic trees. 8. PERFORMANCE REQUIREMENTS: 3D Mech View maintains 60fps on integrated graphics for assemblies up to 30 parts (draco-compressed GLTF/binary STL, instanced fasteners). First token from any agent within 3 seconds on the reference 12GB-VRAM machine. Vector retrieval queries under 200ms at 100k embeddings. docker compose up to first successful chat round-trip in under 15 minutes on a clean machine including model pulls. 9. LICENSING HYGIENE: Every CAD asset row stores its license and source URL. Only redistributable/CC-licensed parts ship in the seed library. Reject ingestion of assets without an identifiable license.

| Schema | Producer → Consumer |
| --- | --- |
| PartRecord, CadAssetRecord (incl. matingFeatures shape) | You → B, C |
| MatingSelection (symbolic: feature IDs + fastener, zero coordinates) | C → B |
| AssemblyTransform (position, quaternion, parentFrame; Z-up, parent-relative) | B → C |
| TemplateParams (per-template bounds) | C → B |
| StepPlan, Lesson, Checkpoint, AgentProgressEvent (SSE) | C → UI/DB (this subset = code C1) |
| RetrievalQuery / RetrievalResult (citations mandatory) | You → C |
| IngestUpsert | seed script / n8n → You |
| Fixture STLs: ESP32, BME280, enclosure, bracket | B → shared (lands with B1) |

### Done when

- Constitution + schemas + mocks + fixtures are on main; three feature branches exist; G1 and C1 are Done.

## A2 — Spec-kit prompts + compose skeleton (Day 1 afternoon)

| When | Day 1 PM |
| --- | --- |
| Wait for | G1 (hard) |
| Unblocks | A3 |
| Merge to main? | No — stays on feature/001-platform-data |
| Tracker | Set A2 → Done (H11) when postgres + ollama boot |

Why it matters: this turns your spec into an executable plan and gets the two foundation services booting, so Day 2 is pure build.

### Do this

- On your branch, in Codex: run $speckit-specify and paste the platform spec below, verbatim.

- Run $speckit-plan and paste the plan prompt below, verbatim.

- Run $speckit-tasks. Review the generated list and reorder if needed so compose + migrations + schemas come before ingestion and retrieval. Then apply the week’s pruning (callout below).

- Run $speckit-implement, steering it at today’s slice only: "implement the compose skeleton tasks — infra/docker-compose.yml with postgres (pgvector image) and ollama (GPU passthrough)". Review the diff, commit.

- Goal for EOD: docker compose up boots postgres + ollama cleanly.

NOTE — Pruning the task list for the 1-week MVP — the spec deliberately describes the full feature; the tracker defines this week. Cut or defer: the n8n service and all scheduled pipelines (weekly iFixit/YouTube, nightly Octopart — Day 3 seeds via a script instead), the **health dashboard *page* (a JSON `/api/health` endpoint is the Day-4 requirement; the page is stretch), and live smoke-test polish. Keep: compose, migrations, schemas package, model-init, the openscad service (B consumes it Day 3), the ingest upsert endpoint** (your seed script uses it), retrieval, and mocked-Ollama CI.

Prompt — paste after $speckit-specify (verbatim) Build the platform and data foundation for a self-hosted educational hardware-building app. This feature delivers everything the other two subsystems (spatial/3D and AI agents) stand on, but no user-facing product features itself. WHAT IT PROVIDES: 1. A one-command local deployment: a single docker-compose brings up the web app, database, local AI model server, workflow engine, and 3D compile service on a user's machine, including first-run model downloads and a health dashboard showing GPU memory and which models loaded. Target: clean machine to working AI round-trip in under 15 minutes. 2. The system of record: a single relational database holding users, projects, build steps, lessons, checkpoint answers, a canonical parts catalog with electrical specs and licensing info, per-user part inventories, 3D asset metadata including physical mating features, assembly transforms, and text embeddings for semantic search. Semantic search must be filterable by relational facts (e.g., only return guidance chunks relevant to parts the user owns). 3. The shared contract package: typed, validated schemas for every payload that crosses a subsystem boundary, plus mock implementations and fixture data that the other two developers build against. 4. Background knowledge ingestion: scheduled pipelines that pull repair guides (weekly), transcripts from a curated video channel list (weekly), and part prices (nightly), plus on-demand datasheet PDF ingestion, all normalized, chunked, embedded, and written through one versioned upsert API. Pipelines never touch the database directly. 5. CI that runs without a GPU: lint, typecheck, unit and contract tests against recorded fixtures. OUT OF SCOPE: any UI beyond the health dashboard, agent logic, 3D geometry processing, lesson content.

Prompt — paste after $speckit-plan (verbatim) Monorepo with pnpm workspaces: apps/web (Next.js 14+ App Router, TS), packages/schemas (zod schemas + mocks + fixtures), infra/ (compose, init scripts, n8n workflow exports), ingestion/ (Python scripts invoked by n8n). Compose services: web, postgres (pgvector/pgvector image), ollama (NVIDIA GPU passthrough; ROCm variant documented), n8n, openscad (headless, exposed as an internal HTTP compile endpoint for the spatial subsystem), model-init container (pulls llama3.2:3b, llama3.1:8b, qwen2.5-coder:7b, nomic-embed-text). Migrations with drizzle-kit. Embeddings via Ollama nomic-embed-text on CPU. VRAM detection endpoint that reports recommended model tier. n8n workflows call POST /api/ingest/v1/upsert with IngestUpsert payloads; the endpoint validates with zod and upserts transactionally. Retrieval endpoint: POST /api/retrieve accepting RetrievalQuery, executing pgvector cosine similarity joined with relational filters, returning RetrievalResult with source citations. Health dashboard at /health as a minimal server-rendered page. GitHub Actions: lint, typecheck, vitest unit + contract suites with mocked Ollama; a separate make target for live GPU smoke tests excluded from CI.

### Done when

- docker compose up → postgres healthy, ollama list answers inside the container.

- spec.md, plan.md and the pruned tasks.md are committed on your branch.

## A3 — Migrations + model-init + schemas package → MERGE (Day 2)

| When | Day 2 — merge to main by end of day |
| --- | --- |
| Wait for | A2 |
| Unblocks | B and C switch from local schema copies to your real package; B4 (soft — the openscad container) |
| Merge to main? | Yes — PR reviewed by B or C |
| Tracker | Set A3 → Done (H14) when the merge lands; announce it |

Why it matters: after this merge the whole team shares one source of truth for types and one migrated database shape. Every day it slips, B and C accumulate drift against stale local copies.

### Do this

- Continue $speckit-implement on the migration tasks: drizzle-kit migrations for the core tables — users, projects, project_steps, lessons, checkpoint_answers, parts_catalog, user_inventory, cad_assets, embeddings (pgvector column), assembly_transforms.

- Add the model-init container (pulls llama3.2:3b, llama3.1:8b, qwen2.5-coder:7b, nomic-embed-text) and the headless openscad service exposing an internal HTTP compile endpoint — B consumes it tomorrow (B4). B has a local-binary fallback, but do not lean on that.

- Verify model-init on the demo machine’s GPU today — first-run pulls are slow and GPU passthrough bugs surface here, not on Day 6.

- Polish packages/schemas: replace G1’s TODO defaults with real types; keep mocks/fixtures in sync in the same commit.

- Open the PR, get a quick review from B or C, merge by EOD, announce in the team channel so B and C rebase.

HARD WAIT — If A3 is slipping past Day 3 morning, tell B and C immediately — that is the tracker’s schema-drift alarm. Do not go quiet and grind.

### Done when

- Fresh clone + docker compose up → migrated DB, models pulled, openscad service answers.

- B and C import packages/schemas from main (confirmed at next standup); A3 Done in tracker.

## A4 — Curate and seed the knowledge corpus (Day 3)

| When | Day 3 |
| --- | --- |
| Wait for | A3 (hard — the DB must exist); C2 (soft) — align chunks to C’s golden StepPlan |
| Unblocks | A5 |
| Merge to main? | No |
| Tracker | Set A4 → Done (H17) |

SOFT WAIT — C2 was due Day 1 EOD, so it should already be Done. If it is somehow late, do not stall: curate generic ESP32/BME280 chunks now and align them to the fixture’s lessons later.

Why it matters: retrieval quality is the ceiling on lesson quality. With small local models, retrieval carries the accuracy burden — the corpus you curate today is what makes C’s lessons true and citable.

### Do this

- Read C’s golden StepPlan fixture and list what its 12–15 steps actually claim (wiring, power, mounting, safety). Curate ~50 chunks to cover those claims: ESP32 pinout and power limits, BME280 I2C wiring and specs, soldering and LiPo safety, enclosure/bracket assembly guidance.

- Every chunk gets a source citation (iFixit guide URL, datasheet section, video timestamp) — the UI will display these, and the constitution requires them.

- Write an idempotent seed script that sends chunks through POST /api/ingest/v1/upsert (constitution principle 5: pipelines never touch tables directly), embeds via nomic-embed-text on CPU, and lands pgvector rows. If the upsert endpoint is not ready yet, a direct drizzle seed is the pragmatic fallback — leave a TODO to reroute it through the API.

- Run it; spot-check with SQL that chunks + embeddings + citations are all present.

### Done when

- ≥ 50 embedded, cited chunks in the DB; the seed script re-runs cleanly (idempotent).

## A5 — Retrieval API + health endpoint → MERGE (Day 4) — your biggest deadline

| When | Day 4 — merge to main by end of day, no exceptions |
| --- | --- |
| Wait for | A4 |
| Unblocks | G2 — Day 5 cannot happen without this. Hard gate. |
| Merge to main? | Yes |
| Tracker | Set A5 → Done (H20) |

Why it matters: this is the tracker’s "most important deadline of the week" for you. Integration day swaps C’s mock retrieval for this endpoint — if it is not on main tonight, Day 5 collapses. Drop anything else to hit it (chunk count, health page, polish).

### Do this

- Build POST /api/retrieve: accepts RetrievalQuery, runs pgvector cosine top-k joined with relational filters (e.g., restrict to parts in the user’s inventory), returns RetrievalResult with mandatory citations. Target < 200ms.

- Build GET /api/health: JSON reporting DB status, which Ollama models are loaded, and detected VRAM / recommended model tier. (The rendered /health *page* is stretch — skip unless ahead.)

- Acceptance test before the PR: the query "connect BME280 to ESP32" returns relevant, cited chunks. If it returns junk, fix chunking/embedding now — C debugs prompts against this tomorrow.

- CI green (mocked-Ollama suites), open PR, review, merge by EOD, announce.

### Done when

- The BME280→ESP32 curl test passes against a fresh docker compose up.

- Merged to main; A5 Done. B5 and C5 should be landing the same evening — nudge if the tracker shows them open.

## A6 — Merge FIRST in the train (Day 5, morning)

| When | Day 5, first thing |
| --- | --- |
| Wait for | A5 + B5 + C5 all Done (hard) — check the tracker, not vibes |
| Unblocks | B6 (B is literally waiting on you) |
| Merge to main? | Yes — first of three, order is A6 → B6 → C6 |
| Tracker | Set A6 → Done (H23) the second it lands |

Why the train: platform first, then the subsystem B built on it, then the subsystem C built on both. One direction, one conflict-resolution pass each. B and C rebase while waiting their turn.

- Rebase feature/001-platform-data on main; resolve anything from B5/C5’s Day-4 merges.

- Merge. Then immediately fix any schema/migration drift: run migrations against a clean DB, run the contract tests.

- Mark A6 Done and say so out loud — B merges next while you stay on call for drift issues.

## A7 — Your share of integration day: seams 1–2 + demo reset (Day 5) [tracker code: G2]

| When | Day 5, after the merge train (A6 → B6 → C6 complete) |
| --- | --- |
| Wait for | C6 Done |
| Unblocks | G3 — rehearsals cannot start until all six seams are closed |
| Merge to main? | Integration PRs may fix seams, not add scope |
| Tracker | No A7 row exists — when all six seams are closed and C has made the live/fixture call, set G2 → Done (H26) |

How G2 runs: on a fresh branch feature/004-integration off main, you type the integration spec below ($speckit-specify), then $speckit-tasks; the generated checklist drives the afternoon. Pairs: you + C on seams 1–2, B + C on seams 3–5, seam 6 is C’s with everyone nearby. Work $speckit-implement in pairs against that list.

Prompt — paste after $speckit-specify on feature/004-integration (you type this, verbatim) Integrate three independently built subsystems - platform/data, spatial/3D, and agents/UX - into one working product, replacing every mock with its real implementation, and verify the complete golden path on real hardware. INTEGRATION SEAMS TO CLOSE (in order): 1. Agents' mock retrieval -> real retrieval API backed by ingested guide content. 2. Agents' mock inventory/parts repository -> real database tables. 3. Assembly agent's mock solver -> real deterministic solver, including the failure loop: solver collision reports must flow back into the agent's retry prompt and produce a corrected mating selection. 4. Workshop's fixture transforms -> real solver-computed transforms rendered in the real 3D viewer, synced per step. 5. Template parameter mock -> real compile/validate loop, including rejection paths surfacing readable errors in the UI. 6. Recorded model fixtures -> live local models on the reference GPU machine. ACCEPTANCE: (a) docker compose up on a clean 12GB-VRAM machine reaches a working app in under 15 minutes; (b) one person who did not build the agents completes the ESP32 weather station end-to-end using only the app, with every 3D transform originating from the solver and every lesson claim carrying a citation; (c) all Socratic checkpoints gate correctly server-side; (d) a full mocked CI run and a live GPU smoke run both pass; (e) kill-switch drills: stopping the model server mid-build degrades to the deterministic fallback content instead of crashing. OUT OF SCOPE: new features. Integration PRs may fix seams, not add scope.

### Your seams (pair with C)

- Seam 1 — mock retrieval → real `/api/retrieve`. Real chunks are messier than C’s canned fixtures; sit with C while they adjust lesson prompts against real output. Citation display gets honest here.

- Seam 2 — mock inventory/parts repo → real tables. C’s SQL joins now hit your real user_inventory / parts_catalog.

### Then, before EOD

- Demo reset script (scripts/demo-reset.sh): wipe + reseed + warm models in under 1 minute. You will run this before every rehearsal and before the live demo.

- Kill-switch drill: stop the Ollama container mid-build — the app must degrade to fixture content (the DEMO_SAFE_MODE path), never crash. This is acceptance item (e) and it is yours.

- Support B and C’s seams when yours close early — G2 is Done as a team or not at all.

## A8 — Demo ops + the backup recording (Day 6) [tracker code: G3]

| When | Day 6 |
| --- | --- |
| Wait for | G2 (hard) |
| Unblocks | G4 — never enter Day 7 without the recording |
| Merge to main? | No |
| Tracker | No A8 row — when both rehearsals + recording are done (and B’s print started), set G3 → Done (H27) |

- On the actual demo machine: pre-pull all four models, run the reset script, verify DEMO_SAFE_MODE toggles end-to-end (a pinned step serves fixture content instantly).

- Run rehearsal 1 with the team and record it (screen + audio) as the backup video. Store it in two places (local + drive/cloud). If rehearsal 1 goes badly, the fallback is capturing it in rehearsal 2 — at the latest.

- Run rehearsal 2 with fixes applied. Time each segment against the Day-7 rundown (A 2 min / C 5–6 min / B 3–4 min).

- Confirm B’s 3D print started in the morning; confirm C’s live-vs-fixture pinning still holds on this machine.

## G4 — Presentation day (Day 7) [tracker: H28]

- You open — 2 minutes: the local-first pitch. Privacy, zero inference cost, accuracy-over-generation ("the LLM never emits a coordinate"), one docker compose up.

- During C’s demo you run ops: reset script beforehand; DEMO_SAFE_MODE within reach — if a live step misbehaves, you flip it silently and C keeps talking; backup video cued in a second window.

- Hand off to B for the 3D moment; be ready to bring the health endpoint / model list on screen if asked "is this really local?".

# 5. Quick reference

## 5.1 Your wait gates

| Before starting | Wait until Done | Hard / Soft | Fallback if late |
| --- | --- | --- | --- |
| G1 | A1 | Hard | None — A1 has no fallback |
| A4 | A3 · C2 | A3 hard · C2 soft | Generic ESP32/BME280 chunks, align later |
| A6 | A5 + B5 + C5 | Hard | Slip integration start; protect merge order |
| A8 | G2 | Hard | Pin unreliable steps to fixture via DEMO_SAFE_MODE |

## 5.2 Who is waiting on YOU

| Your code | Who is blocked until it is Done |
| --- | --- |
| A1 | Everyone — nothing starts before this |
| A3 (merge) | B and C (real schema package); B4 wants your openscad container |
| A5 (merge) | Integration day itself (hard gate for G2) |
| A6 (merge) | B6, then C6 — the whole train |

## 5.3 Your cut list (what to drop if behind — in this order)

- Health dashboard *page* (keep the JSON endpoint) → n8n service and scheduled pipelines (already out of the week) → chunk count 50 → 30 → CI polish.

- Never cut: the A3 and A5 merges, citations on retrieval results, the merge-train order, the backup recording.

## 5.4 Daily rhythm (adapted for a 7-day sprint)

Your source playbooks were written with a multi-week cadence ("twice-weekly contract standup", "rebase every 2 days"). Compressed to one week, the rhythm is:

- Daily 10-minute standup, first thing. Agenda item 1, every day: *"does packages/schemas need to change?"* Item 2: read the tracker’s Blocked counter out loud.

- Rebase your feature branch on `main` every morning, and again immediately after each of A’s merges lands (A3 on Day 2, A5 on Day 4). On Day 5 you rebase while waiting for your merge-train slot.

- Tracker discipline: update column H the minute a task finishes; check it before starting anything with a wait gate.

- Contract-change protocol: packages/schemas is frozen except by PR reviewed by all three, with mocks and fixtures updated in the same PR, announced at standup. A silent schema change is the fastest way to lose Day 5.

## 5.5 DEMO_SAFE_MODE — what it is (everyone must understand this)

An environment flag built by Person C inside the callModel helper (C3). Behavior:

- Flag OFF (normal): every agent call runs live against local Ollama → JSON-schema validate → one retry with the validation error injected → typed fallback to the golden-fixture content if it still fails.

- Flag ON (safe): any step pinned as "fixture" serves the hand-written golden StepPlan content directly, without calling the live model at all.

- Day 5 EOD (C7): C decides live-vs-fixture per step based on how the seams behaved. Day 6 (A8): A verifies the toggle works end-to-end on the demo machine. Day 7 (G4): the toggle sits within A’s reach during the demo — flipping it mid-demo is A’s job, silently.

## 5.6 Escalation ladder

- Blocked on a wait gate more than 30 minutes past when it was due → ping the owner directly, then say it at standup.

- A hard-gate task slipping past its day → announce immediately and apply the fallback listed in its task block; do not silently work late and hope.

- A3 slipping past Day 3 morning is a schema-drift alarm for the whole team (A must announce it).

- Anything threatening the Day 4 merges (A5 / B5 / C5) → cut scope from your cut list, never the merge itself. The merge train and G2 are the week; features are negotiable.

- You are also the team’s tiebreaker: contested schema fields, merge-order disputes, and "cut or keep" calls land on you. Decide fast; the tracker rewards motion.

# Appendix A — Code → tracker map

The Tracker sheet lists 22 tasks (rows 7–28, with A1 anchored at row 7 as the sheet’s own example states). Update column H only; everything else (progress %, per-person stats, blocked counts) recalculates automatically. Row numbers below assume the tracker as shipped — if rows get inserted, trust the code, not the row.

| Code | Row (Status cell) | Owner | Day | Merge to main? |
| --- | --- | --- | --- | --- |
| A1 | H7 | A | Day 1 AM | Yes |
| G1 | H8 | ALL | Day 1 AM | Yes |
| B1 | H9 | B | Day 1 (by lunch) | Yes |
| C1 | H10 | C | Day 1 AM (inside G1) | No |
| A2 | H11 | A | Day 1 PM | No |
| B2 | H12 | B | Day 1 PM | No |
| C2 | H13 | C | Day 1 (by EOD) | Yes |
| A3 | H14 | A | Day 2 | Yes |
| B3 | H15 | B | Day 2 | No |
| C3 | H16 | C | Day 2 | No |
| A4 | H17 | A | Day 3 | No |
| B4 | H18 | B | Day 3 | No |
| C4 | H19 | C | Day 3 | No |
| A5 | H20 | A | Day 4 | Yes |
| B5 | H21 | B | Day 4 | Yes |
| C5 | H22 | C | Day 4 | Yes |
| A6 | H23 | A | Day 5 AM | Yes |
| B6 | H24 | B | Day 5 AM | Yes |
| C6 | H25 | C | Day 5 AM | Yes |
| G2 | H26 | ALL | Day 5 | No (seam fixes only) |
| G3 | H27 | ALL | Day 6 | No |
| G4 | H28 | ALL | Day 7 | No |

NOTE — Codes A7/B7/C7 = each person’s share of G2 (mark H26 Done only when all six seams are closed). Codes A8/B8/C8 = each person’s share of G3 (mark H27 Done only after both rehearsals, the backup recording, and the 3D print have started/finished as specified). The tracker’s "Unblocks" column already references A8/B8/C8 this way — do not add new rows mid-sprint; the sheet’s formulas assume 22 tasks.

# Appendix B — Clarifications baked into this guide

Where your source documents disagreed or left gaps, this guide resolves them as follows (agreed reconciliation, so all three guides match):

- Days, not weeks. Your playbook’s "Week 0–6" table describes the full feature roadmap; the tracker’s Day 1–7 schedule is the operational truth for this sprint. This guide is day-based; the week table’s content is folded into the day tasks and the pruning callouts.

- A7/A8 have no tracker rows. They are your named share of G2 and G3; mark H26/H27 instead.

- Toolchain standardized on Codex CLI (--ai codex, $speckit-* in skills mode). Your playbook’s mixed /speckit.xxx, $speckit.constitution, and --ai claude references all mean the same commands — the notation box in section 0 is the single convention now.

- n8n is out of the 1-week scope. Seeding (A4) goes through the versioned upsert API via a script, honoring constitution principle 5; the scheduled pipelines return post-MVP.

- /health page vs endpoint. The JSON /api/health endpoint is the Day-4 requirement; the rendered dashboard page is stretch.

- Branch protection vs speed. 1-review protection stays on; pre-arrange your reviewer for each merge point (A3, A5, A6) so review latency never eats a deadline; enforce_admins=false is your emergency bypass.