PERSON B — ANI

Spatial & 3D Lead

1-Week MVP Execution Guide · Educational Hardware Builder (OpenAI Week Project)

Toolchain: OpenAI Codex CLI + GitHub Spec-Kit · Companions: mvp-task-tracker.xlsx + Blueprint v2

# 0. Read me first — how this guide works

This guide merges your two source documents (your playbook and your step-by-step timeline) with the two team references (Blueprint v2 and mvp-task-tracker.xlsx) into one self-sufficient runbook for the 7-day sprint. If you follow this document top to bottom, keep the tracker updated, and respect the wait gates, your slice of the project gets built and the three slices integrate on Day 5.

### The code system

- Every task in the sprint has a code. Yours are the B-codes; G-codes (G1–G4) are tasks all three of you do together. Codes map 1:1 to rows in the Tracker sheet of mvp-task-tracker.xlsx (full map in Appendix A).

- Do your codes in order. Never start a task until every code listed under its "Wait for" shows Done in the tracker (column H).

- The moment you finish a task, set its Status cell (column H) to Done — the progress bars and "Blocked" counters update automatically, and someone is usually waiting on you.

- Codes B7 and B8 appear in your timeline but have no rows of their own in the tracker — they are your named share of the group tasks G2 (Day 5 integration) and G3 (Day 6 rehearsals). This guide keeps the codes for clarity and tells you exactly which tracker cell to update instead. G2 and G3 only flip to Done when every person’s share is complete.

### Wait-gate legend

- HARD WAIT — do not start, full stop, until the listed code is Done. Doing the work anyway creates rework and merge conflicts.

- SOFT WAIT — start on time using the listed fallback if the dependency is late, then reconcile when it lands.

### Merge points

You merge to main at three points: B1 (Day 1 by lunch — fixture STLs + expected outputs + mock solver; your most time-sensitive handoff of the week), B5 (Day 4 EOD — the MechView viewer; hard gate for Day 5), and B6 (Day 5 morning — second in the merge train, immediately after A6). G1 also lands on main with the whole team.

### Toolchain notation (Codex CLI + Spec-Kit)

NOTE — This guide writes Spec-Kit commands as /speckit.xxx. The team default agent is OpenAI Codex CLI in skills mode, where the same commands are invoked as $speckit-xxx — e.g. /speckit.specify becomes $speckit-specify — followed by the exact same prompt text. If anyone prefers Claude Code, the /speckit.xxx form works there as-is. If your Codex build does not show the commands, the prompt files live in .codex/prompts/ in the repo — open the file and paste its contents plus your prompt text into the chat (older Codex builds also pick up prompts copied into ~/.codex/prompts/).

### The 7-day map (whole team)

| Day | Theme | Codes in play |
| --- | --- | --- |
| Day 1 | Foundation and contracts | A1 → G1 (incl. C1) → B1 by lunch → A2, B2 (PM) → C2 by EOD |
| Day 2 | Core engines | A3 (merge), B3, C3 |
| Day 3 | Depth | A4, B4, C4 |
| Day 4 | Feature-complete + merges | A5, B5, C5 — all three merge to main (hard gate for Day 5) |
| Day 5 | Merge train + integration | A6 → B6 → C6, then G2: close all six seams (A7/B7/C7) |
| Day 6 | Rehearsals | G3: two full run-throughs + backup recording + 3D print (A8/B8/C8) |
| Day 7 | Presentation | G4: A opens, C drives demo, B owns the 3D moment |

Why the week is shaped this way: Days 1–4 are deliberately parallel — the Day-1 contract sprint (G1) freezes the interfaces so each of you can build against mocks and fixtures without waiting on each other. Day 4 EOD, all three feature branches must be merge-ready; Day 5 morning is a strict merge train (A → B → C) so conflicts are resolved once, in one direction; the rest of Day 5 replaces every mock with the real implementation (the six "seams"). Days 6–7 are pure de-risking: rehearse, record a backup, present.

# 1. Your mission and your week at a glance

Mission: the spatial accuracy engine — the part of the product that guarantees nothing physically wrong is ever shown to a user. Hand-authored CAD mating metadata, the deterministic mating solver, the L-bracket parametric template with its compile/validate loop, and the React Three Fiber 3D viewer. Highest technical risk in the project, and zero LLM dependency — you can build and test everything alone against fixture files.

Your subsystem in one sentence: an AI agent tells you *symbolically* which features of which parts mate; you deterministically compute *exactly how* they fit, validate it, and render it at 60fps.

Your headline: your solver and viewer are the demo’s wow factor — but your most urgent deliverable is your first one: B1 by lunch on Day 1 unblocks Person C for the whole week.

| Code | When | Task | Waits for | Unblocks | Merge? |
| --- | --- | --- | --- | --- | --- |
| — | Day 1, hour 1 | Install prerequisites while A1 runs (you cannot clone yet) | A1 (hard) | — | — |
| G1 | Day 1, hrs 2–3 | Contract sprint — your schemas: matingFeatures, MatingSelection, AssemblyTransform, TemplateParams | A1 | All parallel work | Yes |
| B1 | Day 1 by LUNCH | 4 fixture STLs + expected outputs + mock solver → main | G1 | C5 (hard) — C’s Day 4 | Yes |
| B2 | Day 1 PM | Spec-kit prompts + hand-author metadata for 5 parts | G1 | B3 | No |
| B3 | Day 2 | Finish 10-part metadata + build THE SOLVER + golden tests | B1, B2 | B4, B5 | No |
| B4 | Day 3 | L-bracket template + compile/validate loop | B3; A3 (soft) | B5 | No |
| B5 | Day 4 | MechView viewer + step sync → MERGE | B3, B4 | G2 (hard gate) | Yes |
| B6 | Day 5 AM | Merge SECOND (rebase while A6 runs) | A6 | C6 | Yes |
| B7* | Day 5 | Close seams 3–5 with C (*your share of G2) | Merge train done | G2 → Done | No |
| B8* | Day 6 | Perf pass + camera path + START THE 3D PRINT (*share of G3) | G2 | G4 | No |
| G4 | Day 7 | Own the 3D moment (3–4 min) + hand out the printed bracket | G3 | — | No |

# 2. How you will use Codex + Spec-Kit this week

Spec-Kit turns Codex from a chat assistant into a spec-driven build pipeline. You run its stages in order inside a Codex session launched from the repo root. Each stage writes real artifacts into the repo (under .specify/ and your feature directory), so the work is reviewable and resumable.

| Stage | Command (Codex skills mode) | What it produces / how you use it this week |
| --- | --- | --- |
| Constitution | $speckit-constitution | Project-wide non-negotiable principles. Run once, by Person A, during G1. Every later stage checks itself against it. |
| Specify | $speckit-specify | Your feature spec (the WHAT and WHY). You paste the prepared prompt from this guide — it is already written; do not improvise it. |
| Plan | $speckit-plan | The technical plan (the HOW): stack, packages, structure. Again, paste the prepared prompt. |
| Tasks | $speckit-tasks | An ordered, dependency-aware task list. Review and prune it — the spec describes the full feature; the tracker defines this week. Pruning notes are in your task blocks below. |
| Analyze (optional) | $speckit-analyze | Cross-checks spec / plan / tasks for gaps before you build. Worth 5 minutes if time allows. |
| Implement | $speckit-implement | Codex executes the task list. In this sprint, treat it as a steered pair-programmer, not a one-shot: run it after Tasks, point it at the current day’s slice ("do tasks 1–4: the compose skeleton"), review every diff, commit at each passing checkpoint, and resume the next day. Never let it run unattended past a merge deadline. |

NOTE — One-time setup: specify init was run by Person A with --ai codex, so the command files ship inside the repo — cloning is all B and C need. specify check verifies your local tools. If a command is missing or misbehaves, specify self upgrade updates the CLI; regenerating command files is Person A’s call, not yours.

# 3. Day 0 + Day 1 hour 1 — set up while A1 runs

You are hard-blocked until Person A pushes the repo (A1). Spend Day 0 evening and Day 1’s first hour making your environment fully ready so B1 can hit its lunch deadline:

# uv (Python tool manager) — needed by spec-kit curl -LsSf https://astral.sh/uv/install.sh ¦ sh # OpenAI Codex CLI (the team agent) — then sign in with your ChatGPT account npm install -g @openai/codex codex login # verify afterwards: codex --version # Node 20+, pnpm, git + GitHub CLI, Docker npm install -g pnpm gh auth login # verify: gh auth status

- Your extras: a local openscad binary (fast dev iteration before A’s containerized service exists — and your built-in B4 fallback), Python trimesh (uv pip install trimesh numpy, in a venv is fine), and optionally Blender for eyeballing fixture STLs.

- No Ollama needed — your subsystem has zero LLM dependency. Do not spend your disk or time on model pulls.

- Prepare B1’s raw material now: locate or model the 4 fixture STLs (ESP32 board, BME280, enclosure, bracket) and hand-compute their expected solver outputs on paper — hole positions from datasheets, mate them by hand, write down expected position + quaternion. When the repo opens you just commit.

NOTE — Logistics you own before Day 6: book a 3D printer and confirm filament for Day 6 morning (B8) — the L-bracket print takes hours and the printed part is your Day-7 prop. Also identify the "worst laptop you can find" for MechView perf testing (the constitution’s 60fps target is measured on integrated graphics, not your dev box).

When A announces A1: git clone git@github.com:<org>/hardware-builder.git && cd hardware-builder && pnpm install. Spec-Kit command files ship in-repo (.codex/); the specify CLI itself is optional for you.

# 4. Day-by-day playbook

## G1 — Contract sprint: your non-negotiables (Day 1, hours 2–3)

| When | Day 1, hours 2–3 — timeboxed to 2 hours |
| --- | --- |
| Wait for | A1 (hard) |
| Unblocks | All parallel work; specifically your B1 commit |
| Merge to main? | Yes — schemas + mocks + fixtures land on main |
| Tracker | A marks G1 → Done (H8); C marks C1 |

A types the constitution (you push hardest on principles 1 — accuracy over generation — and 8 — 60fps / 30 parts — you live under both). Then the schema co-authoring, which is your most important meeting. Walk in with these settled in your head and do not leave without them in code:

- `CadAssetRecord.matingFeatures` — you define the shape: holes (id, position, diameter, axis), connector locations, bounding box. Everyone else consumes it.

- `MatingSelection` (C’s agent → your solver) — insist on explicit fastener spec and feature IDs only. Zero coordinates, zero prose fields. The constitution forbids C’s models from emitting coordinates at all; the schema must make it impossible.

- `AssemblyTransform` (your solver’s output) — position, quaternion, parentFrame. Settle the coordinate convention NOW: Z-up, parent-relative — and write it into the schema doc comment. This is the classic 3D integration burn and it is yours to prevent. Enforce it in every code review this week.

- `TemplateParams` — per-template zod bounds you will enforce *before* compilation.

Then branch: git checkout -b feature/002-spatial-3d && git push -u origin feature/002-spatial-3d.

## B1 — Fixture STLs + expected outputs + mock solver → main (Day 1, by LUNCH)

| When | Day 1, hard deadline: lunch |
| --- | --- |
| Wait for | G1 |
| Unblocks | C5 (hard). C’s Day-4 assembly agent is dead in the water without your mock solver |
| Merge to main? | Yes — straight to main via a quick PR (grab A or C for the 1-review rule) |
| Tracker | Set B1 → Done (H9) and message C directly |

Why it matters: this is your most time-sensitive handoff of the week. C builds four days of agent work against this mock; A aligns fixtures to it. Ship it small and correct, not big and late.

### Do this

- Commit the 4 fixture STLs — ESP32 board, BME280, enclosure, bracket — under packages/schemas/fixtures/ (binary STL). If sourcing a clean mesh drags, simplified placeholder geometry with correct hole positions is fine — the hole metadata drives the solver, not mesh beauty. Record license + source for each (constitution principle 9).

- Commit your hand-computed expected solver outputs (expected/*.json): for each known mating of the fixtures, the exact AssemblyTransform you computed on paper. These become the golden files for B3’s tests.

- Commit the mock solver in packages/schemas/mocks/: given a known MatingSelection over the fixtures, return the fixture transform; unknown input → a representative typed SolverError. Same signature the real solver will have.

- Also commit mock matingFeatures JSON for the 4 fixtures (C and the MechView sandbox consume it).

- PR → 1-minute review → main. Mark B1 Done (H9), tell C in person/DM: "mock solver is on main."

### Done when

- C can import the mock solver and fixtures from main and call it with a sample MatingSelection.

- Every fixture STL row has license + source recorded.

## B2 — Spec-kit prompts + metadata for 5 parts (Day 1 afternoon)

| When | Day 1 PM |
| --- | --- |
| Wait for | G1 (B1 should already be Done) |
| Unblocks | B3 |
| Merge to main? | No — stays on feature/002-spatial-3d |
| Tracker | Set B2 → Done (H12) |

### Do this

- On your branch, in Codex: $speckit-specify → paste the spatial spec below, verbatim.

- $speckit-plan → paste the plan prompt below, verbatim.

- $speckit-tasks → review the order: feature extraction → solver → templates/validation → MechView (each earlier piece produces the fixtures the next consumes). Then apply the week’s pruning (callout below).

- $speckit-implement, steered at today’s slice: hand-author `matingFeatures` metadata for 5 of the 10 weather-station parts — transcribe hole positions and diameters from datasheets into the schema. Do NOT write detection code. Hand-authored metadata is the ground truth this week.

NOTE — Pruning the task list for the 1-week MVP — the spec text describes the full feature; the tracker defines the week. Cut or defer: the trimesh auto-detection CLI (deliverable 1 — you hand-author metadata instead; keep trimesh only for the *validation* checks in the scad-service), 4 of the 5 templates (the week builds the L-bracket only, B4), the 30-part seed library (the week uses 10 parts), and Storybook if the /sandbox route is faster. Keep: the solver with full test rigor, the L-bracket compile/validate loop, MechView with all listed interactions, the draco conversion script.

Prompt — paste after $speckit-specify (verbatim) Build the spatial accuracy engine and 3D viewer for an educational hardware-building app. This subsystem guarantees that everything the user sees about how parts physically fit together is deterministically computed from real geometry, never generated by an AI as free text. WHAT IT PROVIDES: 1. CAD ingestion: given a curated 3D model file of a real part (e.g., an ESP32 board), extract its physical mating features (mounting hole positions and diameters, connector locations, bounding box) into structured metadata. Seed library: ~30 license-checked parts covering one weather-station project. 2. A deterministic mating solver: given a symbolic mating selection produced elsewhere ("motor holes A1-A4 mate with bracket holes B1-B4 using M3x8 fasteners"), compute the exact position and rotation that assembles the two parts, and detect invalid selections (mismatched hole counts, incompatible spacing) and physical collisions (bounding-box intersection), returning machine-readable failure reports. 3. A parametric part generator: 5 hand-authored templates (L-bracket, adapter plate, standoff array, enclosure box + lid, sensor mount) that accept a bounded parameter object and produce a printable, validated 3D file. Out-of-bounds parameters, compile failures, and degenerate geometry (zero volume, non-manifold) are rejected automatically with reasons. 4. An interactive 3D assembly viewer component: loads part models, applies computed transforms, supports orbit/pan/zoom, an exploded-view slider, per-step camera focus, and highlighting of specified parts. Maintains 60fps on integrated graphics up to 30 parts. Consumed by the Workshop screen built by another developer, so it must work standalone in a component sandbox against fixture data. DEVELOPED AGAINST FIXTURES: this feature must be fully buildable and testable using committed fixture files and mock data, with no dependency on the AI agents or live database. OUT OF SCOPE: choosing which parts mate (an AI agent does that elsewhere), lesson content, any tab UI besides the viewer component itself.

Prompt — paste after $speckit-plan (verbatim) Three deliverables in the monorepo. (1) ingestion/cad_features: Python + trimesh CLI that reads binary STL, detects circular hole features and bounding boxes, emits CadAssetRecord.matingFeatures JSON conforming to packages/schemas; unit-tested against the committed fixture STLs. (2) packages/solver: pure TypeScript, zero runtime deps beyond a small matrix/quaternion lib (or hand-rolled); input MatingSelection + two CadAssetRecords, output AssemblyTransform or a typed SolverError (mismatch/collision with details); property-based tests plus golden-file tests against fixture expected outputs. (3) assets/templates: 5 OpenSCAD files with documented parameters; packages/scad-service: thin client that validates TemplateParams with per-template zod bounds, POSTs to the headless OpenSCAD compile endpoint (mocked in dev via a local openscad binary or recorded outputs), then validates the resulting STL with a trimesh check script (volume > 0, manifold). (4) apps/web/components/MechView: React Three Fiber + drei; props are fully typed (parts: {cadAssetUrl, transform}[], highlightIds, explodeFactor, cameraTarget); developed in Storybook (or a /sandbox route) against mock AssemblyTransform fixtures; draco-compressed GLTF conversion script for the seed library; instanced meshes for fasteners. All schemas imported from packages/schemas — never redefined locally.

### Done when

- 5 of 10 parts have complete, schema-valid matingFeatures JSON; spec/plan/tasks committed on your branch.

## B3 — Finish the metadata + build THE SOLVER (Day 2)

| When | Day 2 |
| --- | --- |
| Wait for | B1, B2 |
| Unblocks | B4 and B5 |
| Merge to main? | No |
| Tracker | Set B3 → Done (H15) |

Why it matters: the tracker calls this "the demo’s accuracy engine." Everything the audience sees about parts fitting together is this code.

### Do this

- Finish matingFeatures for all 10 weather-station parts (datasheet transcription, same as yesterday).

- Build packages/solver — pure TypeScript, zero runtime deps beyond a small matrix/quaternion lib (or hand-rolled). Input: MatingSelection + two CadAssetRecords. Output: AssemblyTransform or a typed SolverError.

- Error taxonomy with details an 8B model can act on: MISMATCHED_HOLE_COUNT (expected vs actual), INCOMPATIBLE_SPACING (the two spacings, in mm), BOUNDING_BOX_COLLISION (which parts, overlap volume/axis). You will tune the wording with C on Day 5 — design the payloads for that now.

- Tests: golden-file tests against your B1 expected outputs, plus a property test — the solved transform actually aligns mated hole centers within tolerance.

### Done when

- All golden-file tests pass; the property test passes across the fixture set; all 10 parts’ metadata is schema-valid.

## B4 — L-bracket template + compile/validate loop (Day 3)

| When | Day 3 |
| --- | --- |
| Wait for | B3; A3 (soft) — A’s headless OpenSCAD container |
| Unblocks | B5 |
| Merge to main? | No |
| Tracker | Set B4 → Done (H18) |

SOFT WAIT — A3 provides the containerized OpenSCAD compile endpoint — but your fallback is built into the plan: point the scad-service at your local `openscad` binary and do not stall. Swap to the container whenever it lands.

### Do this

- Write assets/templates/l_bracket.scad with documented parameters (arm lengths, thickness, hole spacing, hole diameter, clearances).

- Build packages/scad-service: validate TemplateParams against per-template zod bounds → compile (container endpoint or local binary) → validate the resulting STL with the trimesh check (volume > 0, manifold).

- Rejection paths, each with a machine-readable reason: OUT_OF_BOUNDS (which param, allowed range), COMPILE_FAILED (compiler stderr), DEGENERATE_MESH (which check failed). Tests must cover all three (constitution principle 6).

- Wire it so C’s coder-model TemplateParams step can call it through the mock/real seam later.

CUT LIST — The tracker’s explicit rule: if you are behind on Day 3, cut B4 before B5 — never the solver or the viewer. A demo without the printed bracket survives; a demo without MechView does not.

### Done when

- Out-of-bounds params, a forced compile failure, and a zero-volume mesh are all rejected with machine-readable reasons; happy path emits a printable STL.

## B5 — MechView 3D viewer + step sync → MERGE (Day 4) — your hard gate

| When | Day 4 — merge to main by end of day |
| --- | --- |
| Wait for | B3, B4 |
| Unblocks | G2 — hard gate. Day 5 cannot happen without it |
| Merge to main? | Yes |
| Tracker | Set B5 → Done (H21) |

### Do this

- Build apps/web/components/MechView on the `/sandbox` route against fixture transforms: React Three Fiber + drei.

- Features: STL/GLTF loading (draco-compressed; run your conversion script on the 10 parts), orbit/pan/zoom (drei OrbitControls), exploded-view slider (interpolate each part along its assembly vector), part highlighting, per-step camera targets, instanced meshes for fasteners.

- Props are fully typed and are the contract C consumes: parts: {cadAssetUrl, transform}[], highlightIds, explodeFactor, cameraTarget. Import types from packages/schemas — never redefine locally.

- Perf check: render the full 10-part assembly smoothly — and test on the worst laptop you found, not your dev machine (60fps on integrated graphics is the constitution target).

- PR, review, merge by EOD, announce, mark B5 Done (H21).

### Done when

- /sandbox renders the 10-part weather-station assembly smoothly with all interactions, from fixture data alone.

- Merged to main; A5 and C5 should be landing the same evening.

## B6 — Merge SECOND in the train (Day 5, morning)

| When | Day 5 AM |
| --- | --- |
| Wait for | A6 (hard) — A merges first, always |
| Unblocks | C6 — C is waiting on you exactly as you waited on A |
| Merge to main? | Yes — second of three |
| Tracker | Set B6 → Done (H24) immediately |

- While A6 runs: rebase feature/002-spatial-3d on main and resolve locally.

- The moment A6 is Done: merge. Run the solver golden tests against main to confirm nothing drifted.

- Mark B6 Done and say so out loud — C merges next.

## B7 — Your share of integration day: seams 3–5 with C (Day 5) [tracker code: G2]

| When | Day 5, after the merge train |
| --- | --- |
| Wait for | C6 Done |
| Unblocks | G3 |
| Merge to main? | Integration PRs fix seams, never add scope |
| Tracker | No B7 row — when all six seams are closed, the team sets G2 → Done (H26) |

A types the feature-004 integration spec (the exact text lives in A’s guide); $speckit-tasks produces the seam checklist. Pairs: A + C take seams 1–2; you + C take seams 3–5; seam 6 (live models) is C’s. Your seams:

- Seam 3 — mock solver → `packages/solver`. Sit with C and tune your SolverError messages so C’s retry prompt can act on them — include the numbers (expected vs actual spacing, colliding part IDs). The collision → retry → corrected-MatingSelection loop is a headline demo moment: script one deliberately wrong selection so it can be shown live.

- Seam 4 — fixture transforms → live solver transforms rendered in the real MechView, synced per step in the Workshop.

- Seam 5 — template mock → real compile/validate loop, with rejection reasons surfacing readably in the UI (not raw stderr).

- Before end of day: add the debug assert/log that every rendered transform traces back to a solver call — this is how the team proves acceptance item (b): zero LLM-emitted coordinates.

## B8 — Perf pass + camera path + START THE 3D PRINT (Day 6) [tracker code: G3]

| When | Day 6 — the print starts in the morning, first thing |
| --- | --- |
| Wait for | G2 (hard) |
| Unblocks | G4 |
| Merge to main? | No |
| Tracker | No B8 row — G3 (H27) flips Done after both rehearsals + recording + your print is underway |

- Morning, before anything else: start 3D-printing the L-bracket from the system-generated STL — it takes hours (printer + filament were booked on Day 0). The printed part is your Day-7 physical proof.

- Perf pass: run MechView on the actual demo machine; verify smooth interaction on its GPU/integrated graphics; fix any hitches now.

- Rehearse your exact exploded-view camera path until it is muscle memory — which step you sync to, where the highlight lands, when the slider moves.

- Join both full rehearsals (G3). A records rehearsal 1 as the backup video.

## G4 — Presentation day: you own the 3D moment (Day 7) [tracker: H28]

- Your segment — 3–4 minutes, after C’s main demo: the exploded view, the step-synced highlight, the collision → retry story ("the AI proposed a mate; the solver rejected it with the exact spacing error; the AI corrected itself"), and the template compile loop.

- The closer: hand the printed L-bracket to the audience — "this exact part was parameterized by a local model, validated and compiled deterministically, and printed overnight."

- Keep the /sandbox route open in a tab as your own fallback if the Workshop route misbehaves.

# 5. Quick reference

## 5.1 Your wait gates

| Before starting | Wait until Done | Hard / Soft | Fallback if late |
| --- | --- | --- | --- |
| Anything at all | A1 | Hard | None — install prerequisites + prep B1 material while waiting |
| B4 | A3 (openscad container) | Soft | Local openscad binary (built into your plan) |
| B6 | A6 | Hard | Rebase while waiting |
| B8 | G2 | Hard | Pin unreliable steps to fixture via DEMO_SAFE_MODE |

## 5.2 Who is waiting on YOU

| Your code | Who is blocked until it is Done |
| --- | --- |
| B1 | Person C’s assembly agent (C5) — hard. Also A’s fixture alignment and the MechView sandbox data |
| B5 (merge) | Integration day itself (hard gate for G2) |
| B6 (merge) | C6 — the last car of the merge train |

## 5.3 Your cut list (in this order) and your guard list

- Cut first: B4 (the template + compile loop) → extra fixture STLs beyond 4 → Storybook (use /sandbox) → draco polish. Never cut: the solver, its tests, or MechView — the tracker is explicit: "cut the bracket template, NEVER the solver or viewer."

- Guard list (things only you can screw up): coordinate-convention drift (it lives in the schema doc comment — enforce in review); hole-metadata typos from datasheet transcription (double-enter and diff); MechView perf judged on your dev machine instead of the worst laptop.

## 5.4 Daily rhythm (adapted for a 7-day sprint)

Your source playbooks were written with a multi-week cadence ("twice-weekly contract standup", "rebase every 2 days"). Compressed to one week, the rhythm is:

- Daily 10-minute standup, first thing. Agenda item 1, every day: *"does packages/schemas need to change?"* Item 2: read the tracker’s Blocked counter out loud.

- Rebase your feature branch on `main` every morning, and again immediately after each of A’s merges lands (A3 on Day 2, A5 on Day 4). On Day 5 you rebase while waiting for your merge-train slot.

- Tracker discipline: update column H the minute a task finishes; check it before starting anything with a wait gate.

- Contract-change protocol: packages/schemas is frozen except by PR reviewed by all three, with mocks and fixtures updated in the same PR, announced at standup. A silent schema change is the fastest way to lose Day 5.

## 5.5 DEMO_SAFE_MODE — what it is (everyone must understand this)

An environment flag built by Person C inside the callModel helper (C3). Behavior:

- Flag OFF (normal): every agent call runs live against local Ollama → JSON-schema validate → one retry with the validation error injected → typed fallback to the golden-fixture content if it still fails.

- Flag ON (safe): any step pinned as "fixture" serves the hand-written golden StepPlan content directly, without calling the live model at all.

- Day 5 EOD (C7): C decides live-vs-fixture per step based on how the seams behaved. Day 6 (A8): A verifies the toggle works end-to-end on the demo machine. Day 7 (G4): the toggle sits within A’s reach during the demo — flipping it mid-demo is A’s job, silently.

## 5.6 Escalation ladder

- Blocked on a wait gate more than 30 minutes past when it was due → ping the owner directly, then say it at standup.

- A hard-gate task slipping past its day → announce immediately and apply the fallback listed in its task block; do not silently work late and hope.

- A3 slipping past Day 3 morning is a schema-drift alarm for the whole team (A must announce it).

- Anything threatening the Day 4 merges (A5 / B5 / C5) → cut scope from your cut list, never the merge itself. The merge train and G2 are the week; features are negotiable.

# Appendix A — Code → tracker map

The Tracker sheet lists 22 tasks (rows 7–28, with A1 anchored at row 7 as the sheet’s own example states). Update column H only; everything else (progress %, per-person stats, blocked counts) recalculates automatically. Row numbers below assume the tracker as shipped — if rows get inserted, trust the code, not the row.

| Code | Row (Status cell) | Owner | Day | Merge to main? |
| --- | --- | --- | --- | --- |
| A1 | H7 | A | Day 1 AM | Yes |
| G1 | H8 | ALL | Day 1 AM | Yes |
| B1 | H9 | B | Day 1 (by lunch) | Yes |
| C1 | H10 | C | Day 1 AM (inside G1) | No |
| A2 | H11 | A | Day 1 PM | No |
| B2 | H12 | B | Day 1 PM | No |
| C2 | H13 | C | Day 1 (by EOD) | Yes |
| A3 | H14 | A | Day 2 | Yes |
| B3 | H15 | B | Day 2 | No |
| C3 | H16 | C | Day 2 | No |
| A4 | H17 | A | Day 3 | No |
| B4 | H18 | B | Day 3 | No |
| C4 | H19 | C | Day 3 | No |
| A5 | H20 | A | Day 4 | Yes |
| B5 | H21 | B | Day 4 | Yes |
| C5 | H22 | C | Day 4 | Yes |
| A6 | H23 | A | Day 5 AM | Yes |
| B6 | H24 | B | Day 5 AM | Yes |
| C6 | H25 | C | Day 5 AM | Yes |
| G2 | H26 | ALL | Day 5 | No (seam fixes only) |
| G3 | H27 | ALL | Day 6 | No |
| G4 | H28 | ALL | Day 7 | No |

NOTE — Codes A7/B7/C7 = each person’s share of G2 (mark H26 Done only when all six seams are closed). Codes A8/B8/C8 = each person’s share of G3 (mark H27 Done only after both rehearsals, the backup recording, and the 3D print have started/finished as specified). The tracker’s "Unblocks" column already references A8/B8/C8 this way — do not add new rows mid-sprint; the sheet’s formulas assume 22 tasks.

# Appendix B — Clarifications baked into this guide

Where your source documents disagreed or left gaps, this guide resolves them as follows (agreed reconciliation, so all three guides match):

- Days, not weeks. Your playbook’s "Week 0–6" table is the full-feature roadmap; the tracker’s Day 1–7 schedule is operational truth. This guide is day-based.

- B7/B8 have no tracker rows — they are your named share of G2 and G3; mark H26/H27 instead.

- Fixture count standardized: your playbook said "4–6 files"; the tracker and B1 say 4 (ESP32, BME280, enclosure, bracket). Four named files is the deadline; extras are welcome, not required.

- Template scope: the spec text lists 5 templates and a 30-part library; this week ships the L-bracket and 10 parts. The spec stays as written (it describes the feature); the $speckit-tasks output gets pruned.

- No detection code this week: the trimesh feature-*detection* CLI from your plan is deferred; metadata is hand-authored (B2/B3). Trimesh is still used for scad-service mesh *validation*.

- Toolchain standardized on Codex CLI — $speckit-* in skills mode; /speckit.xxx is the same command in Claude Code.

- Logistics made explicit: printer + filament booked Day 0; worst-laptop perf target; /sandbox as your personal demo fallback.