PERSON C — ARVEEN

Agents & Workshop UX Lead

1-Week MVP Execution Guide · Educational Hardware Builder (OpenAI Week Project)

Toolchain: OpenAI Codex CLI + GitHub Spec-Kit · Companions: mvp-task-tracker.xlsx + Blueprint v2

# 0. Read me first — how this guide works

This guide merges your two source documents (your playbook and your step-by-step timeline) with the two team references (Blueprint v2 and mvp-task-tracker.xlsx) into one self-sufficient runbook for the 7-day sprint. If you follow this document top to bottom, keep the tracker updated, and respect the wait gates, your slice of the project gets built and the three slices integrate on Day 5.

### The code system

- Every task in the sprint has a code. Yours are the C-codes; G-codes (G1–G4) are tasks all three of you do together. Codes map 1:1 to rows in the Tracker sheet of mvp-task-tracker.xlsx (full map in Appendix A).

- Do your codes in order. Never start a task until every code listed under its "Wait for" shows Done in the tracker (column H).

- The moment you finish a task, set its Status cell (column H) to Done — the progress bars and "Blocked" counters update automatically, and someone is usually waiting on you.

- Codes C7 and C8 appear in your timeline but have no rows of their own in the tracker — they are your named share of the group tasks G2 (Day 5 integration) and G3 (Day 6 rehearsals). This guide keeps the codes for clarity and tells you exactly which tracker cell to update instead. G2 and G3 only flip to Done when every person’s share is complete.

### Wait-gate legend

- HARD WAIT — do not start, full stop, until the listed code is Done. Doing the work anyway creates rework and merge conflicts.

- SOFT WAIT — start on time using the listed fallback if the dependency is late, then reconcile when it lands.

### Merge points

You merge to main at three points: C2 (Day 1 EOD — spec/plan/tasks scaffolding + the hand-written golden StepPlan fixture), C5 (Day 4 EOD — the full agent pipeline + gated Workshop, on mocks; a hard gate for Day 5), and C6 (Day 5 morning — you merge last in the train, after A6 then B6). G1 also lands on main with the whole team.

### Toolchain notation (Codex CLI + Spec-Kit)

NOTE — This guide writes Spec-Kit commands as /speckit.xxx. The team default agent is OpenAI Codex CLI in skills mode, where the same commands are invoked as $speckit-xxx — e.g. /speckit.specify becomes $speckit-specify — followed by the exact same prompt text. If anyone prefers Claude Code, the /speckit.xxx form works there as-is. If your Codex build does not show the commands, the prompt files live in .codex/prompts/ in the repo — open the file and paste its contents plus your prompt text into the chat (older Codex builds also pick up prompts copied into ~/.codex/prompts/).

### The 7-day map (whole team)

| Day | Theme | Codes in play |
| --- | --- | --- |
| Day 1 | Foundation and contracts | A1 → G1 (incl. C1) → B1 by lunch → A2, B2 (PM) → C2 by EOD |
| Day 2 | Core engines | A3 (merge), B3, C3 |
| Day 3 | Depth | A4, B4, C4 |
| Day 4 | Feature-complete + merges | A5, B5, C5 — all three merge to main (hard gate for Day 5) |
| Day 5 | Merge train + integration | A6 → B6 → C6, then G2: close all six seams (A7/B7/C7) |
| Day 6 | Rehearsals | G3: two full run-throughs + backup recording + 3D print (A8/B8/C8) |
| Day 7 | Presentation | G4: A opens, C drives demo, B owns the 3D moment |

Why the week is shaped this way: Days 1–4 are deliberately parallel — the Day-1 contract sprint (G1) freezes the interfaces so each of you can build against mocks and fixtures without waiting on each other. Day 4 EOD, all three feature branches must be merge-ready; Day 5 morning is a strict merge train (A → B → C) so conflicts are resolved once, in one direction; the rest of Day 5 replaces every mock with the real implementation (the six "seams"). Days 6–7 are pure de-risking: rehearse, record a backup, present.

# 1. Your mission and your week at a glance

Mission: everything the learner sees and talks to — the multi-agent pipeline, the five-tab Workshop UI, the Socratic checkpoints, and the golden path: one weather-station project that works end to end, every time, on stage. You own the demo narrative.

Your subsystem in one sentence: you turn a natural-language request into a grounded, cited, step-by-step, gated build experience — orchestrating A’s retrieval and B’s spatial engine without ever letting a model invent a fact or a coordinate.

Your headline: you build the entire week against mocks (A’s mock retrieval, B’s mock solver, the mock template service), so you are almost never hard-blocked mid-week — but you inherit the golden-path fixture as ground truth, and you drive the demo, so your Day-5 live-vs-fixture decisions are the whole team’s safety net.

| Code | When | Task | Waits for | Unblocks | Merge? |
| --- | --- | --- | --- | --- | --- |
| — | Day 1, hour 1 | Install prerequisites + pull 4 models while A1 runs | A1 (hard) | — | — |
| G1 (+C1) | Day 1, hrs 2–3 | Contract sprint — you author the agent-facing schemas (this IS tracker C1) | A1 | All parallel work | Yes |
| C2 | Day 1 by EOD | Spec/plan/tasks scaffold + hand-write the golden StepPlan → main | G1 | Your whole week; A4 (soft) | Yes |
| C3 | Day 2 | The callModel helper + Router/Research/Lesson on mock retrieval | C2 | C4 | No |
| C4 | Day 3 | Split-screen Workshop + server-side checkpoint gating | C3 | C5 | No |
| C5 | Day 4 | Assembly agent + full flow on mocks → MERGE | C4; B1 (hard) | G2 (hard gate) | Yes |
| C6 | Day 5 AM | Merge LAST (wait A6 → B6) | B6 | G2 seams | Yes |
| C7* | Day 5 | Close all six seams + decide live-vs-fixture per step (*your share of G2) | Merge train done | Rehearsals | No |
| C8* | Day 6 | Tune 8B prompts + write demo script + drive both rehearsals (*share of G3) | G2 | G4 | No |
| G4 | Day 7 | Drive the demo (5–6 min) — you are the main presenter | G3 | — | No |

# 2. How you will use Codex + Spec-Kit this week

Spec-Kit turns Codex from a chat assistant into a spec-driven build pipeline. You run its stages in order inside a Codex session launched from the repo root. Each stage writes real artifacts into the repo (under .specify/ and your feature directory), so the work is reviewable and resumable.

| Stage | Command (Codex skills mode) | What it produces / how you use it this week |
| --- | --- | --- |
| Constitution | $speckit-constitution | Project-wide non-negotiable principles. Run once, by Person A, during G1. Every later stage checks itself against it. |
| Specify | $speckit-specify | Your feature spec (the WHAT and WHY). You paste the prepared prompt from this guide — it is already written; do not improvise it. |
| Plan | $speckit-plan | The technical plan (the HOW): stack, packages, structure. Again, paste the prepared prompt. |
| Tasks | $speckit-tasks | An ordered, dependency-aware task list. Review and prune it — the spec describes the full feature; the tracker defines this week. Pruning notes are in your task blocks below. |
| Analyze (optional) | $speckit-analyze | Cross-checks spec / plan / tasks for gaps before you build. Worth 5 minutes if time allows. |
| Implement | $speckit-implement | Codex executes the task list. In this sprint, treat it as a steered pair-programmer, not a one-shot: run it after Tasks, point it at the current day’s slice ("do tasks 1–4: the compose skeleton"), review every diff, commit at each passing checkpoint, and resume the next day. Never let it run unattended past a merge deadline. |

NOTE — One-time setup: specify init was run by Person A with --ai codex, so the command files ship inside the repo — cloning is all B and C need. specify check verifies your local tools. If a command is missing or misbehaves, specify self upgrade updates the CLI; regenerating command files is Person A’s call, not yours.

# 3. Day 0 + Day 1 hour 1 — set up while A1 runs

You are hard-blocked on the repo until A1, but you have the heaviest local-model setup on the team — do it Day 0 evening so nothing downloads on the clock:

# uv (Python tool manager) — needed by spec-kit curl -LsSf https://astral.sh/uv/install.sh ¦ sh # OpenAI Codex CLI (the team agent) — then sign in with your ChatGPT account npm install -g @openai/codex codex login # verify afterwards: codex --version # Node 20+, pnpm, git + GitHub CLI, Docker npm install -g pnpm gh auth login # verify: gh auth status

Install Ollama natively (not in Docker — you want GPU acceleration for dev) and pull all four models up front:

# native Ollama, then pull every model your pipeline routes to ollama pull llama3.2:3b # Router + simple extraction ollama pull llama3.1:8b # Lesson prose + reasoning ollama pull qwen2.5-coder:7b # TemplateParams (custom parts) ollama pull nomic-embed-text # embeddings (shared with A)

- You need a GPU dev machine (the same 12–16GB VRAM class A is booking for the demo box). Confirm access Day 0 — your Day-2 callModel work needs live models running.

- When A announces A1: git clone … && cd hardware-builder && pnpm install, then git checkout -b feature/003-agents-workshop.

# 4. Day-by-day playbook

## G1 + C1 — Contract sprint: you author the agent-facing schemas (Day 1, hours 2–3)

| When | Day 1, hours 2–3 |
| --- | --- |
| Wait for | A1 (hard) |
| Unblocks | All parallel work |
| Merge to main? | Yes — schemas + mocks land on main |
| Tracker | This meeting is your C1 (H10) — mark it Done here; A marks G1 (H8) |

NOTE — C1 has no separate work block — your Day-1 schema authoring during the contract sprint *is* tracker task C1. This guide folds them together on purpose so you don’t go looking for a C1 that lives elsewhere.

A types the constitution; you own the agent-output schemas and must win two fights in the room:

- Mandatory citations. Every Research/Lesson output field that states a fact carries a citation reference. Bake it into the schema so an un-cited claim fails validation (constitution principle 3).

- Symbolic MatingSelection only. With B, lock MatingSelection to feature IDs + fastener spec, no coordinates, no prose. The models physically cannot emit geometry if the schema won’t hold it (principle 1). This is the single most important schema decision for your demo’s credibility.

You also define, with the team consuming them: `StepPlan`, `Lesson`, `Checkpoint`, and the `AgentProgressEvent` SSE payload. Sketch the golden weather-station fixture on the whiteboard in this meeting — it will save you Day 1 evening. Then branch: git checkout -b feature/003-agents-workshop.

## C2 — Scaffold + hand-write the golden StepPlan → MERGE (Day 1, by EOD)

| When | Day 1, by end of day |
| --- | --- |
| Wait for | G1 |
| Unblocks | Your entire week; A4 (soft) — A aligns real chunks to your golden path |
| Merge to main? | Yes — the golden fixture belongs to everyone |
| Tracker | Set C2 → Done (H13) and tell A the golden path is on main |

### Do this

- On your branch in Codex: $speckit-specify → paste the agents/workshop spec below (verbatim). $speckit-plan → paste the plan (verbatim). $speckit-tasks. Do NOT `$speckit-implement` yet — today is scaffolding + the fixture.

- Prune the task list for the week (callout below).

- Hand-write the golden StepPlan fixture for the weather station — this is the single most important artifact you produce all week.

- Commit it under apps/web/fixtures/ (it triples as golden path, E2E fixture, and callModel fallback). Merge to main.

NOTE — The golden StepPlan, precisely: 12–15 ordered steps; exactly 3 Socratic checkpoints; every assembly step uses a symbolic MatingSelection built from B’s real part + feature IDs (coordinate with B — these must reference the fixtures from B1); one step invokes a TemplateParams generation (the L-bracket, matching B4); every field must pass zod validation against the schemas you just wrote.

HARD WAIT — Why hand-written, not model-generated: an LLM-authored fixture would quietly smuggle in the exact errors (hallucinated coordinates, missing citations, invalid mates) that this whole architecture exists to prevent — and then your "known-good" fallback would be subtly broken. Author it by hand so ground truth is actually ground truth.

CUT LIST — Pruning for the week: Beginner difficulty only (defer Intermediate/Advanced lesson variants); the weather-station seed project only (Gallery can list just it); Playwright E2E is a stretch — the golden fixture matters more than automated coverage; Inventory/Gallery visual polish is deferrable. Keep: all five tabs present, the full agent state machine, server-side gating, the callModel helper.

Prompt — paste after $speckit-specify (verbatim) Build the agent pipeline and the learner-facing Workshop experience for an educational hardware-building app. This is the part the user actually talks to: they describe a project in natural language and are guided, step by step, through understanding and virtually assembling it, with the app teaching as it goes. WHAT IT PROVIDES: 1. A multi-agent pipeline (a deterministic state machine, not an autonomous free-for-all): a Router classifies the request; a Research agent retrieves grounded, cited information from the knowledge base; a Build planner produces an ordered StepPlan; a Parts agent selects real parts from inventory and justifies substitutions; per step, a Lesson agent writes the teaching content, an Assembly agent emits a SYMBOLIC mating selection (never coordinates) for the spatial solver, and a TemplateParams agent (only when a custom part is needed) emits bounded parameters for the generator. Every agent output is schema-validated; every factual claim carries a citation. 2. A five-tab Workshop UI: Dashboard (start/resume projects), Research (cited findings), Build (the step plan), Parts (inventory + substitutions), and the step-by-step Workshop itself — a split screen pairing the 3D viewer with lesson content, gated Socratic checkpoints, and a completion screen. 3. Socratic checkpoints: at key steps the learner must answer a conceptual question correctly before the next step unlocks. Gating is enforced server-side. Wrong answers get targeted re-explanation, not the answer. 4. A "golden path": one fully authored reference project (a weather station) that always works end to end for the demo, independent of live-model variance. DEVELOPED AGAINST MOCKS: build entirely against the mock retrieval endpoint, mock solver, and mock template service so this is fully testable before real services land. Live models and real services swap in at integration. OUT OF SCOPE: computing physical transforms (the solver does that), generating geometry (the template service does that), the retrieval index internals (the platform owns that).

Prompt — paste after $speckit-plan (verbatim) apps/web owns the Workshop UI and the agent orchestration route. A single callModel helper wraps every LLM call: it takes a schema, calls Ollama with format:"json" for structured outputs, validates with zod, and on failure retries ONCE with the validation error injected into the prompt, then falls back to a committed fixture; a DEMO_SAFE_MODE flag forces the fixture path per-step. Model routing: llama3.2:3b for routing/simple extraction, llama3.1:8b for lesson prose and reasoning, qwen2.5-coder:7b for TemplateParams; temperatures pinned low (<=0.3 for structural output, <=0.7 for prose). The pipeline is an explicit TypeScript state machine (Router -> Research -> Build -> Parts -> per-step[Lesson -> Assembly -> (TemplateParams when needed) -> scad] -> Gallery), each transition validating against packages/schemas. Progress streams to the client via SSE (a ReadableStream emitting typed AgentProgressEvent). Workshop UI in apps/web/app/workshop with Zustand for wizard state and TanStack Query for server state; MechView is embedded via its typed props. Checkpoint gating is enforced in the route handler, not the client. Playwright E2E drives the full golden-path flow. All agent I/O types come from packages/schemas; the golden-path fixture doubles as the E2E fixture and the fallback content.

### Done when

- The golden StepPlan fixture is on main, passes zod validation, and its mating selections reference real B fixture IDs.

- spec/plan/tasks committed; A knows to align real chunks to your golden path (A4).

## C3 — The callModel helper + first agents on mocks (Day 2)

| When | Day 2 |
| --- | --- |
| Wait for | C2 |
| Unblocks | C4 |
| Merge to main? | No |
| Tracker | Set C3 → Done (H16) |

Why it matters: callModel is the reliability spine of the entire product. Every model interaction in the demo flows through it; DEMO_SAFE_MODE lives inside it.

### Do this

- Build the callModel helper: takes a zod schema + prompt → calls Ollama with format:"json" → validates → on failure retries once with the validation error injected into the prompt → still failing, falls back to the committed fixture. A DEMO_SAFE_MODE flag forces the fixture path per-step.

- Pin temperatures: ≤0.3 for structural output, ≤0.7 for prose. Make the Ollama base URL injectable (you’ll point it at the real host at integration).

- Implement Router (3b), Research (8b), and Lesson (8b) agents against A’s mock retrieval endpoint — Research pulls cited chunks; Lesson writes teaching prose with citations preserved.

- Wire the SSE AgentProgressEvent stream so the client can watch the pipeline think.

### Done when

- 20 consecutive live calls each either schema-validate or cleanly fall back — no unhandled failures.

- Citations render in the Research/Lesson output; DEMO_SAFE_MODE forces fixtures when set.

## C4 — Split-screen Workshop + server-side gating (Day 3)

| When | Day 3 |
| --- | --- |
| Wait for | C3 |
| Unblocks | C5 |
| Merge to main? | No |
| Tracker | Set C4 → Done (H19) |

### Do this

- Build the split-screen Workshop route: MechView on one side (embed B’s component via its typed props, fed fixture transforms for now), lesson content + checkpoint on the other, synced to the current step.

- Wire Zustand for wizard/step state and the SSE stream into the UI so progress animates live.

- Implement Socratic checkpoints with server-side gating — the unlock decision lives in the route handler, never the client.

- Stand up the other tabs at MVP depth: Dashboard (start/resume), Research, Build, Parts.

HARD WAIT — Prove the gate is real: hit the API directly (curl/Postman) for step N+1 without passing step N’s checkpoint and confirm you get a 403. A checkpoint that only hides a button in the client is not gating — and a reviewer will ask you to demonstrate this.

### Done when

- Direct API call for a locked step returns 403; the Workshop renders MechView + lesson + checkpoint in step-sync from fixtures.

## C5 — Assembly agent + full flow on mocks → MERGE (Day 4) — your hard gate

| When | Day 4 — merge to main by end of day |
| --- | --- |
| Wait for | C4; B1 (hard) — you need B’s mock solver |
| Unblocks | G2 — hard gate. Day 5 cannot start without it |
| Merge to main? | Yes |
| Tracker | Set C5 → Done (H22) |

HARD WAIT — Before you start, confirm B1 is Done (B’s mock solver on main — it landed Day 1 by lunch). If for any reason it slipped, stub the mock solver behind an identity transform + a flag and keep moving; swap in B’s the moment it lands. Do not let your Day 4 stall on it.

### Do this

- Build the Assembly agent: per step it emits a symbolic MatingSelection (feature IDs + fastener, never coordinates) → your callModel path sends it to B’s mock solver → on a SolverError, retry once with the error injected, exactly like callModel does for schema failures.

- Add a lint/test rule that rejects any numeric position field in agent output — a coordinate leaking out of a model is a build failure, not a runtime surprise (enforces principle 1 mechanically).

- Implement checkpoint grading: correct → unlock; wrong → targeted re-explanation, never the answer.

- Polish Dashboard + completion screen + SSE progress. Run the entire golden-path flow end to end on mocks.

- PR, review, merge by EOD, mark C5 Done (H22).

### Done when

- The full weather-station flow runs start → completion on mocks; the Assembly→solver→retry loop works against B’s mock; coordinate-leak lint is green.

- Merged to main alongside A5 and B5.

## C6 — Merge LAST in the train (Day 5, morning)

| When | Day 5 AM |
| --- | --- |
| Wait for | B6 (hard) — you are car three: A6 → B6 → C6 |
| Unblocks | G2 seam-closing |
| Merge to main? | Yes — last of three |
| Tracker | Set C6 → Done (H25) |

- While A6 and B6 run: rebase feature/003-agents-workshop on main, resolve conflicts locally, keep the golden-path E2E green.

- The moment B6 is Done: merge. Run the full golden-path flow on main to confirm the three subsystems compose.

- Mark C6 Done — the merge train is complete and integration (G2) begins.

## C7 — Integration day: all six seams + the live-vs-fixture call (Day 5) [tracker code: G2]

| When | Day 5, after the merge train |
| --- | --- |
| Wait for | C6 Done |
| Unblocks | G3 rehearsals |
| Merge to main? | Seam fixes only — no new scope |
| Tracker | When all six seams close, the team sets G2 → Done (H26) |

You touch every seam — the mocks being replaced are all yours. Pairs: A + you on seams 1–2; B + you on seams 3–5; you own seam 6.

- Seams 1–2 (with A) — mock retrieval → real `/api/retrieve`, mock inventory → real tables. Real chunks are messier than your fixtures; adjust the Lesson/Research prompts so cited output stays clean on real data.

- Seams 3–5 (with B) — mock solver → real solver, fixture transforms → real transforms, template mock → real compile loop. Tune the collision → retry prompt using B’s real SolverError payloads until the 8B model reliably corrects a bad mate.

- Seam 6 (yours) — recorded fixtures → live models, step by step through the golden path.

HARD WAIT — The decision only you can make — before end of Day 5: for each step, decide live model vs pinned fixture, and pin the choice via DEMO_SAFE_MODE. A step that is flaky under the live 8B gets pinned; a step that is reliably beautiful stays live. Rehearsals (G3) are blocked until this is locked — the team cannot rehearse a demo whose behavior is still changing. Day 5 is never the day you perform live; it is the day you decide what performs live.

## C8 — Tune prompts + write the demo script + drive rehearsals (Day 6) [tracker code: G3]

| When | Day 6 |
| --- | --- |
| Wait for | G2 (hard) |
| Unblocks | G4 |
| Merge to main? | No |
| Tracker | G3 (H27) flips Done after both rehearsals + A’s backup recording |

- Final prompt tuning on the live 8B, watching your retry/fallback counters — anything that leans on fallback too often either gets a better prompt or gets pinned to fixture.

- Write the demo script (you are the narrator): natural-language prompt → plan → parts substitution justification → the gated checkpoint with a scripted wrong answer (show the re-explanation) → B’s collision → retry beat → 3D handoff to B → completion screen.

- Confirm DEMO_SAFE_MODE is within A’s reach for a silent Day-7 toggle if anything wobbles.

- Drive both full rehearsals end to end; A records rehearsal 1 as the backup video.

## G4 — Presentation day: you drive the demo (Day 7) [tracker: H28]

- You are the main presenter — 5–6 minutes, the spine of the whole demo, after A’s 2-minute setup.

- The arc: type a real prompt → watch the plan build (SSE progress live) → show the Parts substitution with justification → hit the gated checkpoint and deliberately answer wrong so the audience sees Socratic re-explanation, then answer right to unlock → cue B’s collision→retry + 3D moment → land on the completion screen.

- If any step wobbles, DEMO_SAFE_MODE (A’s hand on the toggle) silently serves the pinned fixture — the audience never knows. Keep narrating.

# 5. Quick reference

## 5.1 Your wait gates

| Before starting | Wait until Done | Hard / Soft | Fallback if late |
| --- | --- | --- | --- |
| Anything at all | A1 | Hard | Pull all 4 models + read schemas while waiting |
| C5 (assembly agent) | B1 (mock solver) | Hard | Identity-transform stub behind a flag; swap when B1 lands |
| C6 | B6 | Hard | Rebase + keep golden-path E2E green while waiting |
| C8 / rehearsals | G2 (live-vs-fixture locked) | Hard | None — do not rehearse until every step is pinned or confirmed live |

## 5.2 Who is waiting on YOU

| Your code | Who / what is blocked until it is Done |
| --- | --- |
| C2 (golden path) | A4 (soft) — A aligns real ingested chunks to your golden StepPlan; B for the mating-ID coordination |
| C5 (merge) | Integration day (hard gate for G2) |
| C6 (merge) | G2 seam-closing begins |
| C7 (live-vs-fixture) | All of G3 — no rehearsal can start until you lock it |

## 5.3 Your cut list and your guard list

- Cut in this order: Gallery/Inventory visual polish → Playwright E2E automation (keep the fixture) → mastery-scoring nuance on checkpoints → Intermediate/Advanced lesson variants. Never cut: the golden path, server-side gating, or the callModel reliability path — those *are* the demo.

- Guard list (things only you can screw up): a model emitting coordinates or an un-cited fact (the lint + schema catch it — keep them green); client-only gating slipping in under time pressure (always verify the 403); fixtures drifting from the messier live 8B behavior (that is what the Day-5 live-vs-fixture pass is for).

## 5.4 Daily rhythm (adapted for a 7-day sprint)

Your source playbooks were written with a multi-week cadence ("twice-weekly contract standup", "rebase every 2 days"). Compressed to one week, the rhythm is:

- Daily 10-minute standup, first thing. Agenda item 1, every day: *"does packages/schemas need to change?"* Item 2: read the tracker’s Blocked counter out loud.

- Rebase your feature branch on `main` every morning, and again immediately after each of A’s merges lands (A3 on Day 2, A5 on Day 4). On Day 5 you rebase while waiting for your merge-train slot.

- Tracker discipline: update column H the minute a task finishes; check it before starting anything with a wait gate.

- Contract-change protocol: packages/schemas is frozen except by PR reviewed by all three, with mocks and fixtures updated in the same PR, announced at standup. A silent schema change is the fastest way to lose Day 5.

## 5.5 DEMO_SAFE_MODE — what it is (everyone must understand this)

An environment flag built by Person C inside the callModel helper (C3). Behavior:

- Flag OFF (normal): every agent call runs live against local Ollama → JSON-schema validate → one retry with the validation error injected → typed fallback to the golden-fixture content if it still fails.

- Flag ON (safe): any step pinned as "fixture" serves the hand-written golden StepPlan content directly, without calling the live model at all.

- Day 5 EOD (C7): C decides live-vs-fixture per step based on how the seams behaved. Day 6 (A8): A verifies the toggle works end-to-end on the demo machine. Day 7 (G4): the toggle sits within A’s reach during the demo — flipping it mid-demo is A’s job, silently.

## 5.6 Escalation ladder

- Blocked on a wait gate more than 30 minutes past when it was due → ping the owner directly, then say it at standup.

- A hard-gate task slipping past its day → announce immediately and apply the fallback listed in its task block; do not silently work late and hope.

- A3 slipping past Day 3 morning is a schema-drift alarm for the whole team (A must announce it).

- Anything threatening the Day 4 merges (A5 / B5 / C5) → cut scope from your cut list, never the merge itself. The merge train and G2 are the week; features are negotiable.

- You own DEMO_SAFE_MODE’s per-step pinning; A owns the master toggle on stage. If a live step is unreliable at any point after Day 5, the answer is always "pin it to fixture," never "hope it works on stage."

# Appendix A — Code → tracker map

The Tracker sheet lists 22 tasks (rows 7–28, with A1 anchored at row 7 as the sheet’s own example states). Update column H only; everything else (progress %, per-person stats, blocked counts) recalculates automatically. Row numbers below assume the tracker as shipped — if rows get inserted, trust the code, not the row.

| Code | Row (Status cell) | Owner | Day | Merge to main? |
| --- | --- | --- | --- | --- |
| A1 | H7 | A | Day 1 AM | Yes |
| G1 | H8 | ALL | Day 1 AM | Yes |
| B1 | H9 | B | Day 1 (by lunch) | Yes |
| C1 | H10 | C | Day 1 AM (inside G1) | No |
| A2 | H11 | A | Day 1 PM | No |
| B2 | H12 | B | Day 1 PM | No |
| C2 | H13 | C | Day 1 (by EOD) | Yes |
| A3 | H14 | A | Day 2 | Yes |
| B3 | H15 | B | Day 2 | No |
| C3 | H16 | C | Day 2 | No |
| A4 | H17 | A | Day 3 | No |
| B4 | H18 | B | Day 3 | No |
| C4 | H19 | C | Day 3 | No |
| A5 | H20 | A | Day 4 | Yes |
| B5 | H21 | B | Day 4 | Yes |
| C5 | H22 | C | Day 4 | Yes |
| A6 | H23 | A | Day 5 AM | Yes |
| B6 | H24 | B | Day 5 AM | Yes |
| C6 | H25 | C | Day 5 AM | Yes |
| G2 | H26 | ALL | Day 5 | No (seam fixes only) |
| G3 | H27 | ALL | Day 6 | No |
| G4 | H28 | ALL | Day 7 | No |

NOTE — Codes A7/B7/C7 = each person’s share of G2 (mark H26 Done only when all six seams are closed). Codes A8/B8/C8 = each person’s share of G3 (mark H27 Done only after both rehearsals, the backup recording, and the 3D print have started/finished as specified). The tracker’s "Unblocks" column already references A8/B8/C8 this way — do not add new rows mid-sprint; the sheet’s formulas assume 22 tasks.

# Appendix B — Clarifications baked into this guide

Where your source documents disagreed or left gaps, this guide resolves them as follows (agreed reconciliation, so all three guides match):

- Days, not weeks. Your playbook’s "Week 0–6" table is the full-feature roadmap; the tracker’s Day 1–7 schedule is operational truth. This guide is day-based.

- C1 is folded into G1. There is no standalone C1 work block — your schema authoring during the Day-1 contract sprint *is* tracker task C1 (mark H10 there).

- C7/C8 have no tracker rows — they are your named share of G2 and G3; mark H26/H27 with the team.

- Golden path is hand-written, never model-generated — otherwise the fallback inherits the very errors the architecture prevents.

- Week scope: Dashboard + Workshop + completion screen are required; Inventory/Gallery polish and Playwright E2E are stretch. The /api/health JSON endpoint is A’s Day-4 requirement; the /health *page* + Playwright is stretch.

- n8n and scheduled ingestion pipelines are out of scope this week — A seeds chunks via an idempotent script; you consume retrieval through the mock then the real /api/retrieve.

- Toolchain standardized on Codex CLI — $speckit-* in skills mode; /speckit.xxx is the same command in Claude Code.